## Sheet1
Implementation of ANALGESIC STEWARDSHIP (AGS) Program | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Comments
Year 2025 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31
Program Planning (see adaptable Program Plan Template)
Program Plan
Program Aim and Scope
Program Evaluation Plan
Program Governance
Risk Management
Review of Clinical Care Standard
Stakeholder engagement
Stakeholder Identification
Stakeholder engagement plan
Audits
Baseline point prevalence audit (PPA)
PPA analysis and presentation
12 month point prevalence audit (PPA)
Monitoring
Measurement Plan
Data Collection Tool
Governance
AGS Committee - membership planning, key stakeholder identification
Terms of Reference (TOR) development
Committee Selection
Establish regular meeting schedule
AGS Committee Agenda 1
AGS Committee Minutes 1
AGS Committee Agenda 2
AGS Committee Minutes 2
AGS Committee Agenda 3
AGS Committee Minutes 3
Terms of Reference (TOR) annual review
Guidelines
Key Author Identification
Acute Pain/Discharge Guideline Development
Review by AGS Committee and key stakeholders
Guideline Implementation Evaluation
Education
Education material development/endorsement by AGS committee
Education Strategy Planning
Pharmacy Education Sessions
Medication Education Sessions
Nursing Education Sessions
Posters/Newsletter
Education Evaluation
Patient Resources
Discharge Medication Management Plan Development
Analgesic Leaflet Development
Consumer Review of resources
Resource rollout evaluation
Research
Review proposal
Ethics submission
Draft manuscript
Submit manuscript for publication
Evaluation and future planning
Sustainability Plan
Progress Reports
Final Report
Other