Planning for research dissemination

Dissemination plan template

OFFICIAL

Research dissemination involves sharing research findings with the people who can use, influence or benefit from them, including healthcare professionals, policy makers, patients, cares, community organisations and other relevant audiences.

Dissemination planning should begin early in a project. Building engagement throughout the research process can help increase the reach and impact of your findings. Activities may include:

- sharing project updates through a website or newsletter

- inviting people to follow your project on social media

- presenting at conferences and professional events

- engaging stakeholders throughout the project

- sharing preliminary findings and emerging insights, where appropriate, while clearly communicating when findings have not yet been peer reviewed)

A dissemination plan typically identifies:

- key messages

- target audiences

- communication channels and activities

- timeframes

- responsibilities

- measures of success.

This example dissemination plan can be adapted to suit the needs of your project, audience and research context.

# Project title [name of project]

## Key messages

- Message 1

- Message 2

### Target audiences

| Audience/sector | Professional group/organisation | Examples |
| --- | --- | --- |
| e.g. Public | Consumer groups and networks | - Partnering with consumers in health research |
| e.g. Public | e.g. Government and government agencies/policymakers | - National Dept of Health - State Dept of Health - State Safety and Quality Agencies - Drug Regulatory Authorities - Peak medicines bodies |
| e.g. Clinical sector – pharmacy | Therapeutic Advisory Groups; Pharmacy Networks and Hospital Pharmacists; Society Hospital Pharmacists of Australia | - pharmacies/pharmacists co-located in large inpatient settings - Hospital drug committees |

### Information and results

| Information medium | Details | Responsibility | Implemented (date/place) | Success measure |
| --- | --- | --- | --- | --- |
| Publications | - Peer reviewed papers - Final study report | Investigator team, led by the Coordinating Principal Investigator | Drafted awaiting analysis of data, as soon after close to recruitment | Accepted and published Citations |
| Conference presentations | - List conferences | Investigator team, usually the Coordinating Principal Investigator | Some conferences will allow the presentation of research before the results are available, others will only allow presentation of final results | Number of attendees Audience feedback |
| Industry meetings and other face-to-face meetings | - Drug manufacturers - Government Departments of Health - Drug regulatory authority (TGA) - National Medicines Authority/Boards | Investigator team in conjunction with the Communications Officer | As soon as possible after close to recruitment | Attendance by target stakeholders, positive feedback, follow-up engagement and evidence of research uptake. |
| Marketing/promotional materials | - Ministerial Brief - Multimedia presentations - Lay summaries - Targeted newsletter inserts | Marketing/Communications Officer | As soon as possible after close to recruitment | Number distributed and/or downloaded Number of enquires generated |
| Webinar/s | Webinar title | Communications Officer |  | Number of registrations Event survey responses |
| Resource publication | Location of publication e.g. website | Communications Officer |  | Number of downloads within [X] timeframe |

### Social media plan

| Information medium | Details | Responsibility | Implemented (date/place) | Success measure |
| --- | --- | --- | --- | --- |
| Website – research group or project page on organisation website | Home base – all information stored here and all social traffic leads back here* | Communications Officer | First months/year or research | xx views per month |
| Website – personal | As above if not part of larger organisation* | Individual members of the investigator team | To be determined by the individual | xx views per month |
| Blogs | Determine list of industry-specific blog sites that the team can contribute to through the project | Investigation team in conjunction with a content writer | Plan out regular blogs based on project stages/ milestones being achieved | Page views, reader engagement, social media shares and referrals to project resources. |
| Podcast interviews | Find reputable podcasts that focus on your area of research | Investigator team in conjunction with the Communications Officer | Plan searches on a quarterly basis | Impressions and engagements [reposts/comments] |
| YouTube/video interviews | Find reputable channel that focuses on your area of research | Investigator team in conjunction with the Communications Officer | Base interviews on project stages/milestones being achieved | Impressions and engagements [reposts/comments] |
| Twitter or Bluesky | Set up a group or individual Twitter account (or both) | Group or individual | Daily/Weekly/Planned tweets when significant events/information to share | Impressions and engagements [reposts/comments] |
| LinkedIn | Create personal profiles and keep them up to date* | Researcher in conjunction with the Communications Officer | Weekly/monthly/planned posts when significant events/information to share | Impressions and engagements [reposts/comments] |
| Facebook | Create a page with a meaningful lay name that will capture broad audiences | Researcher in conjunction with the Communications Officer | Weekly/monthly/planned posts when significant events/information to share | Impressions and engagements [reposts/comments] |
| Instagram | Create a profile with a meaningful lay name that will capture broad audiences | Researcher in conjunction with the Communications Officer | Weekly/monthly/planned posts when significant events/information to share | Impressions and engagements [reposts/comments] |

Adapted from: Brown LR and James L. How to disseminate palliative care research findings. In: Higginson IJ et al. (eds), Research Methods in Palliative, Supportive, and End-of-Life Care (2nd ed.). Oxford University Press, 2025.

### Further reading: National Health and Medical Research Council, Australian Research Council and Universities Australia. Publication and dissemination of research: a guide supporting the Australian Code for the Responsible Conduct of Research (2020).